## Sheet2
S NUM | PENDING WORK | START DATE | END DATE | STATUS | EXPECTED DATE | EXPECTED DATE (updated on 28-4-14) | EXPECTED DATE (updated on 29-4-14) | EXPECTED DATE (updated on 01-5-14) | EXPECTED DATE (updated on 02-5-14) | EXPECTED DATE (updated on 05-5-14) | S.NUM | PROJECT NAME | EMPLOYEE NAME | WORK(1-5-14) | WORK(2-5-14) | WORK(5-5-14) | S.NUM | EMPLOYEE EMAILD CREATION | EMPLOYEE DETAILS
31 | Documents need to submit the lawyer | 17/02/2014 |  | completed | completed | Today evening Seshu sir will talk to Lawyer | Seshu sir will talk to Ravi sir | Tomorrow(02.05.2014)seshu sir will go to lawyer | seshu sir not meet the lawyer | seshu sir not meet the lawyer | 1 | Wawalive | Sireesh,Siva kumar, Bharath | Sireesha working on wawalive travels module applying routing concept and modified image upload (binary format),Bharath working on forum module pages in visa_ usa pages converting aspx pages to routing pages | Supraja working on wawalive site applying routing concept to header menu of the home page and forums pages in main site,sireesha working on wawalive site applying routing concept for classified pages. In that pages applying classified home page and search categories wise page and view page.,Bharath working on wawalive applying in routing at forums pages |  | 1 | Sowjanya Manglaram | Father’s NAME: M Gangadher, DOJ: 4/2/2014, DOB: 10/02/1991, CONTACT NUM: 8801993591, mail id: sirim411@gmail.com,Address: 7-31/3,Macharla (Vi),Armoor (Ma),Nizamabad (Dt) AP.
30 | Pay pal multiple account | 17/02/2014 |  | Seshu sir talk to support people they said we have to take another account for multiple account |  | Today Seshu sir talk to support people they said we have to take another account for multiple account | Seshu sir talk to support people they said we have to take another account for multiple account | when we require at that time we will take | when we require at that time we will take | when we require at that time we will take | 2 | Indus Travels | Mahalakshmi, Ashoka, Swathisri | Swathisri working on industravels registrationform.aspx page,Ashoka working on industravels contactus.aspx page | Mahalakshmi working on Indus Travel Admin site , postdate ,country columns in packages table ,adding the properties for postdate, country and changed the code in travel packages form according to the postdate, Swathisri working on industravels registrationform.aspx page, Ashoka working on industravels contactus.aspx page |  | 2 | Veeranjaneyulu Yarramsetty | Father’s NAME: Sivaiah, DOJ: 14/11/2013, DOB: 05/03/1985, CONTACT NUM: 9492318816, mail id: anjimca2011@gmail.com,Address: D no-15-65, Sankati bazar, Bhattiprolu (Mad), Guntur (DT). 522256
29 | Pay pal through Internet bank sms | 17/02/2014 |  | Today Seshu sir will talk to support people |  | Seshu sir will talk to support people |  | who having account they only get sms & E Mail | who having account they only get sms & E Mail | who having account they only get sms & E Mail | 3 | igiit | Ravi sirigiri | Ravi working on Pay sheet at igiit admin page | Ravi working on Pay sheet at igiit admin page he will complete today end of the day | Ravi working on Pay sheet at igiit admin page he said completed the workd ,talk to madma | 3 | Sivakumar Padigineti | Father’s NAME: Kodhandaiah,DOJ: 27/11/2013,DOB: 24/09/1990,CONTACT NUM: 8143450764, mail id: Sivakumar.Padigineti@gmail.com,ADdress: Pottempadu (post), Muthukur (Mand), Nellore (Dt). 524346
28 | Employee’s official mail id creation | 17/02/2014 |  | pending (I sent employee's details) (for devlopment team we have to create) |  | ( we have to create mail id's for devlopment team) For recruiters completed | we have to create office mail id's for devlopment team | we have to create office mail id's for devlopment team | we have to create office mail id's for devlopment team | we have to create office mail id's for devlopment team | 4 | Indusedu | Veeranjaneyulu,Jraghuram | Veeranjaneyulu Working on Student admission Form counsel_studentnewform.aspx page and Verifying Marketing emails Prices | Veeranjaneyulu Working on indusedu councel_studentedit.aspx page |  | 4 | Bharath Swamireddygari | Father’s NAME: Raghurami Reddy ,DOJ: 27/11/2013,DOB: 05/06/1991,CONTACT NUM: 8125550970, mail id: bharath3344@gmail.com, ADdress: H no: 1-100, Orvakal (Mand), Kurnool (Dt). 518010
27 | Quick books implementation (Accounts) | 17/02/2014 |  | Vijaya working on( she was started watching demo videos) |  | Seshu sir talk to quick books person tomarrow morning he will come | Today morning quick books peroson(RajKumar Shankari)came, he talk to seshu sir | Tomorrow(02.05.2017) we will convert from Tally to quickbook to talk to Customer care | we are not talk to Customer care | we need to trasfer from tally to quickbooks | 5 | Industimes |  | Supraja working on it_default.aspx to default.aspx in entire website, doing small modifications in entire website |  |  | 5 | Ashoka Thalacheeru | Father’s NAME: Babu ,DOJ: 2/12/2013,DOB: 01/06/1991,CONTACT NUM: 9440332406, mail id: ashokachowdary54@gmail.com,Address: Jagalapalli (Vil), Atmakur (md), Nellore (Dt). 524307
26 | Day shift (Designer, Php ,SEO) | 29/04/2014 |  | SEO completed,Conducting interviews for designers ,PHP hold | SEO will join on 7th April 2014 | SEO joined, For designers conducting interviews (vijaya working on) | For designers conducting interviews (vijaya working on) | (vijaya working on) Today two designers came,we have given templates after that seshu sir spoke to them | (vijaya working on) Today one designer came,we have given template after that seshu sir spoke to her | Today one designer joined, Her name Ramadevi Bodasu |  |  | Sowjanya | Working with development team(preparing images) | Working with development team(preparing images) |  | 6 | Swathisri kurra | Father’s NAME: Krishna rao ,DOJ: 2/12/2013,DOB: 19/08/1991,CONTACT NUM: 7416170991, mail id: sriswathikurra@gmail.com,ADdress: Ithanagr, Tenali, Guntur (Dt).
25 | Night shift (BDM, Recruiter ) | 29/04/2014 |  | Process going on (Tours BDM Joined today (5/3/2014)) , | Night shift BDM will join on 7th April 2014 | conducting interviews (Kalyan working on) | conducting interviews (vijaya working on) | (vijaya working on) | (vijaya working on) | (vijaya working on) |  | Recruting | Kalyan |  |  |  | 7 | Jagadeesh Maraka | Father’s NAME: Madan Mohanrao,DOJ: 9/04/2014,DOB: 16/08/1991,CONTACT NUM: 9494298266, ADdress: D no- 2-46, Nagaram (post & Mad), Guntur (DT). 522268
24 | Sites spell check - | 17/02/2014 |  | Aceindus , Indusemail, Industravels, igiit , careersgen completed , wawalive india completed | penidng US,UK,AUS will be completed on 7th April 2014 | wawalive completed , preparing bulet points for wawalive | SEO Analysis Report (spell check and content updation) Arun kumar working on | wawalive respell checking ( Arun kumar working on) | wawalive respell checking it will complete 2 days ( Arun kumar working on) | wawalive spell check completed, working on description links for indusemail ( Arun kumar working on) |  |  | Keerthika |  |  |  | 8 | Jraghuram Pulipati | Father’s NAME: Pulipati V Narasimharao, DOJ: 17/1/2014,DOB: 03/09/1989,CONTACT NUM: 9963953410, mail id: raghu.pch2008@gmail.com, ADdress: # 1-5-4. Ramkotaih bazar, Barampet, Narasaraopet, Guntur (Dt). 522601
23 | Mnhbs template finalize | 17/02/2014 |  | Prasad working on( http://www.acsglb.com/mnhbs/) | [8 empty] | vijaya |  |  |  | 9 | Saisena Tadakamadla | Father’s NAME:T Raji Reddy ,DOJ: 10/2/2014,DOB: 27/06/1992,CONTACT NUM: 8179619767, mail id: reddysaisena@gmail.com,ADdress: 2-59, Kurikyal (vi), Gangadhara (Md), Karimnagar. AP.505445
22 | Igiit template finalize - | 17/02/2014 |  | template hosted | [12 empty] | 10 | Saikiran Sankati | Father’s NAME: Kishan ,DOJ: 10/2/2014,DOB: 26/11/1990,CONTACT NUM: 9573639326, mail id: sankatisaikiran1226@gmail.com, ADdress: H-no: 6-136, Venkampally, Gangadhara (Md), Karimnagar. AP.
21 | Indus innovations template finalize | 17/02/2014 |  | seshu sir will host some templates ,
20 | Indus vision template finalize | 17/02/2014 |  | seshu sir will host some templates ,
19 | Background verification check for employees | 17/02/2014 |  | Seshu sir will talk |  | Seshu sir will talk | Seshu sir will talk
18 | International business consulting | 17/02/2014 |  | (US office will work) |  | (US office will work) | (US office will work) | (US office will work) | (US office will work) | (US office will work)
17 | Testing report XL sheet (Test Cases) | 17/02/2014 |  | (This weekend we will get from ravi sir) |  | ( we will get from ravi sir) | ( we will get from ravi sir) | ( we will get from ravi sir) | ( we will get from ravi sir) | ( we will get from ravi sir)
16 | PMP (project management) http://pm.igiit.net/pm/index.php?m=projects userneme: admin password: passwd | 17/02/2014 |  | Project names added in pmp, department names added, Raghavedhar working on task assignment to developer. |  | Project names,department names added in pmp, I have added one xl at Files tab at pmp home page under doucuments folder(for testing) | Project names,department names added in pmp, I have added one xl at Files tab at pmp home page under doucuments folder(for testing) | Project names,department names added in pmp, I have added one xl at Files tab at pmp home page under doucuments folder(for testing) | Project names,department names added in pmp, I have added one xl at Files tab at pmp home page under doucuments folder(for testing) | Project names,department names added in pmp, I have added one xl at Files tab at pmp home page under doucuments folder(for testing)
15 | Conrep application | 17/02/2014 |  | pending |  | pending | pending | pending( we will add Recruiting Choice) | pending( we will add Recruiting Choice) | pending( we will add Recruiting Choice)
14 | Travels amadeus training | 22/04/2014 | 25/4/14 | It will take one week time(documents submited) | 8th April 2014 | last week completed on (25/4/14) Surya attended | completed on (25/4/14) Surya attended | completed on (25/4/14) Surya attended | completed on (25/4/14) Surya attended | completed on (25/4/14) Surya attended
13 | Schedule email | 17/02/2014 |  | Working |  | working using elastic email | working using elastic email | working using elastic email | working using elastic email | working using elastic email
12 | Indus email price list | 17/02/2014 |  | Seshu sir will talk |  | Seshu sir will talk | Seshu sir will talk to ravi sir | Seshu sir will talk to ravi sir | Seshu sir will talk to ravi sir | Seshu sir will talk to ravi sir
11 | Indus email browser compatibly | 17/02/2014 |  | Development team working on |  | Raghavedhar rao said it's working for present sites | Raghavedhar rao said it's working for present sites | Raghavedhar rao said it's working for present sites | Raghavedhar rao said it's working for present sites | Raghavedhar rao said it's working for present sites
10 | Madhapur office | 18/02/2014 |  | (Ravi sir will talk to seshu sir) |  | (Ravi sir will talk to seshu sir) | (Ravi sir will talk to seshu sir) | (Ravi sir will talk to seshu sir) | (Ravi sir will talk to seshu sir) | (Ravi sir will talk to seshu sir)
9 | Weekly meeting | 18/02/2014 |  | Every Tuesday (started) |  | Tomarrow(29/4/14) we will conduct the meeting | Today seshu sir talk to designers tomarrow we will conduct the meeting with devlopment team |  |  | Tomarrow(06/5/14) we will conduct the meeting
8 | Employee ID cards | 30/04/2014 | [6 empty] | we have to preparefor new employees | we have to prepare for new employees (we have uploded old emplyee id's in FTP)
7 | Issuing offer letters | 18/02/2014 |  | completed (Not issued) |  | completed (Not issued) | completed (Not issued) | Not issued | Not issued | (we have uploded in FTP)
6 | Travels amount | 26/02/2014 |  | (Ravi sir will talk to seshu sir)(Satish Vemana, Venkat Thalacheeru) |  | (Ravi sir will talk to seshu sir)(Satish Vemana, Venkat Thalacheeru) | (Ravi sir will talk to seshu sir)(Satish Vemana, Venkat Thalacheeru) | (Ravi sir will talk to seshu sir)(Satish Vemana, Venkat Thalacheeru) | (Ravi sir will talk to seshu sir)(Satish Vemana, Venkat Thalacheeru) | (Ravi sir will talk to seshu sir)(Satish Vemana, Venkat Thalacheeru)
5 | RSS Feeds (Indus times) | 26/02/2014 |  | (Sujeet have to do) Seshu sir sent a mail to Sujeet |  | (Sujeet have to do) Seshu sir sent a mail to Sujeet | (Sujeet have to do) Seshu sir sent a mail to Sujeet | (Sujeet have to do) Seshu sir sent a mail to Sujeet | (Sujeet have to do) Seshu sir sent a mail to Sujeet | (Sujeet have to do) Seshu sir sent a mail to Sujeet
4 | Mohan | 26/02/2014 |  | Seshu sir spoke to Mohan(Mohan will arrange the systems next week ending) , |  | Seshu sir spoke to Mohan, first week he will give the cheque | Today Seshu sir make a call to Mohan he was not pickup the call | Seshu sir spoke to Mohan, first week he will give the cheque | Seshu sir spoke to Mohan, first week he will give the cheque | Seshu sir spoke to Mohan, first week he will give the cheque
3 | Internal messenger | 26/02/2014 |  | Raghavedhar rao suggested Tonic internal massager (IP based) But it will work with in the Lan only |  |  |  |  | Raghavedhar rao suggested Miranda communicator(He will arrange 2 days) | Raghavedhar rao suggested Miranda communicator(He will arrange 2 days)
2 | Credit card | 28/02/2014 | 15/3/2014 | Completed | Completed | Completed | Completed | Completed | Completed | Completed
1 | Net banking for Indus travels | 05/03/2014 | 17/3/2014 | Completed | Completed | Completed | Completed | Completed | Completed | Completed